## Risk Register
Asset | Risk Description | Likelihood | Impact | Score | Existing Controls | Risk Owner | Mitigation Plan | Target Date | Status

## Risk Scoring Matrix
Impact | Likelihood | Score
Low | Low | 1
Low | High | 2
High | Low | 3
High | High | 4

## Risk Register Example
Asset | Risk Description | Likelihood | Impact | Score | Existing Controls | Risk Owner | Mitigation Plan | Target Date | Status
Email System | Phishing attack | 4 | 5 | 20 | Spam filter | IT Manager | Deploy MFA | 2026-05-15 | Open
Laptops | Device theft | 3 | 4 | 12 | Disk encryption | IT Manager | Enable remote wipe | 2026-06-01 | Open
CRM Database | Unauthorized access | 3 | 5 | 15 | RBAC | Security Lead | Quarterly access reviews | 2026-05-30 | Open
Cloud Storage | Misconfigured bucket | 4 | 5 | 20 | Logging enabled | Cloud Admin | Audit permissions | 2026-05-20 | Open
VPN | Weak passwords | 3 | 4 | 12 | Password policy | IT Manager | Enforce MFA | 2026-05-10 | Open
Website | SQL injection | 2 | 5 | 10 | WAF | Dev Lead | Code review | 2026-06-10 | Open
HR System | Insider misuse | 2 | 4 | 8 | Access controls | HR Director | Monitoring alerts | 2026-07-01 | Open
Finance App | Ransomware | 3 | 5 | 15 | Backups | CFO | Test recovery | 2026-06-15 | Open
Shared Drives | Excessive permissions | 4 | 4 | 16 | Folder groups | IT Admin | Permission cleanup | 2026-05-25 | Open
Endpoint Devices | Missing patches | 4 | 4 | 16 | Auto-updates | IT Admin | Patch audit | 2026-05-18 | Open
Wi-Fi Network | Rogue access point | 2 | 4 | 8 | WPA3 | Network Admin | Wireless monitoring | 2026-06-20 | Open
Customer Portal | Broken authentication | 3 | 5 | 15 | Session timeout | Dev Lead | Security testing | 2026-06-05 | Open
Backup Server | Backup failure | 3 | 5 | 15 | Daily backup jobs | IT Admin | Monthly restore tests | 2026-05-28 | Open
Third-party Vendor | Vendor breach | 3 | 4 | 12 | Vendor review | Procurement | Annual reassessment | 2026-07-10 | Open
Mobile Phones | Lost device | 3 | 3 | 9 | MDM | IT Manager | Enforce PIN policy | 2026-05-22 | Open
Payroll System | Data leakage | 2 | 5 | 10 | Encryption | HR Manager | DLP deployment | 2026-06-30 | Open
Source Code Repo | Credential exposure | 3 | 5 | 15 | Secret scanning | DevOps | Rotate keys | 2026-05-12 | Open
SaaS Apps | Shadow IT | 4 | 3 | 12 | App inventory | Security Lead | SaaS monitoring | 2026-06-25 | Open
Office Network | Malware spread | 3 | 4 | 12 | Antivirus | IT Admin | Network segmentation | 2026-06-18 | Open
DNS | Domain hijacking | 2 | 5 | 10 | Registrar lock | IT Admin | Enable DNSSEC | 2026-06-08 | Open
Admin Accounts | Privilege abuse | 2 | 5 | 10 | PAM | Security Lead | Session recording | 2026-07-05 | Open
Collaboration Tools | Oversharing files | 4 | 3 | 12 | Sharing limits | Team Lead | User training | 2026-05-26 | Open
USB Devices | Malware infection | 3 | 3 | 9 | Device control | IT Admin | Disable USB | 2026-06-02 | Open
Data Center | Power outage | 2 | 5 | 10 | UPS | Facilities | Generator testing | 2026-07-15 | Open
API Gateway | Token misuse | 3 | 4 | 12 | Token expiry | DevOps | API monitoring | 2026-06-11 | Open
Employee Accounts | Dormant accounts | 4 | 4 | 16 | HR offboarding | HR + IT | Monthly review | 2026-05-29 | Open
Printer | Stored documents exposed | 2 | 3 | 6 | Secure print | Office Admin | PIN printing | 2026-07-01 | Open
Incident Response Plan | Outdated plan | 3 | 4 | 12 | Annual review | Security Lead | Update procedures | 2026-06-07 | Open
Customer Data | Unencrypted exports | 2 | 5 | 10 | Export restrictions | Data Owner | Encrypt exports | 2026-06-16 | Open
Remote Access | Unsecured home networks | 3 | 4 | 12 | VPN | IT Manager | Employee awareness | 2026-06-22 | Open